## ADCP_history
Date | Time(UTC) | Type | Type;Parameters;model;S/N | Comments | Operator | miscellaneous
2020-07-22 | 10:12 | Installation | Workhorse Sentinel ADCP;Surface Current velocity ;WHS600 600kHz;20515 | Deployment | Sébastien Lavanchy | ADCP_Installation schematics.pdf, ADCP_installation.jpg
2020-07-22 | 10:12 | Installation | Workhorse Sentinel ADCP;Deep Current velocity ;WHS300 300kHz;20360 | Deployment | Sébastien Lavanchy | ADCP_Installation schematics.pdf, ADCP_installation.jpg
2020-07-24 | 10:15 | Installation | Workhorse Sentinel ADCP;all;all;all | Online vmdas | Bieito Fernandez | RDI300_vmdas.ini, RDI600_vmdas.ini
2021-06-25 | 7:29 | Issue | Workhorse Sentinel ADCP;all;all;all | ADCP caught in sedtrap line | Guillaume Cunillera | ADCP_sedtrap.jpg
2021-06-25 | 12:00 | Maintenance | Workhorse Sentinel ADCP;all;all;all | Clean biofouling + quagga | Guillaume Cunillera | ADCP_quagga.jpg
2021-06-25 | 17:33 | Repair | Workhorse Sentinel ADCP;all;all;all | ADCP back to water | Sébastien Lavanchy
2021-08-31 | 6:07 | Issue | Workhorse Sentinel ADCP;all;all;all | cable of the ADCP damaged | Philippe Quetin
2021-09-02 | 16:25 | Repair | Workhorse Sentinel ADCP;all;all;all | repaired and molded | Guillaume Cunillera | ADCP_mold.jpg
2022-05-31 | 14:00 | Issue | Workhorse Sentinel ADCP;all;all;all | Mooring slid to South-East. 12m deep | Sébastien Lavanchy
2023-01-04 | 12:00 | Recovery/removal | Workhorse Sentinel ADCP;all;all;all | power turned on for ROV peration and maintenance tomorrow | Sébastien Lavanchy
2023-01-05 | 13:00 | Issue | Workhorse Sentinel ADCP;all;all;all | scratches on the 600 container, decision to send both for revisioin. | Michael Plüss
2023-01-12 | 12:00 | Service Factory | Workhorse Sentinel ADCP;Surface Current velocity ;WHS600 600kHz;20515 | shipment ref : 25337 for the WH 600 SN 20515
2023-01-12 | 12:00 | Service Factory | Workhorse Sentinel ADCP;Deep Current velocity ;WHS300 300kHz;20360 | shipment ref : 25338 for WH 300 SN 20360
2023-01-19 | 10:12 | Installation | Workhorse Sentinel ADCP;Surface Current velocity ;WHS600 600kHz;1178 | Deployment temporary ADCP from EAWAG | Michael Plüss
2023-01-19 | 10:12 | Installation | Workhorse Sentinel ADCP;Deep Current velocity ;WHS300 300kHz;20847 | Deployment temporary ADCP from EAWAG | Michael Plüss
2023-04-03 | 12:00 | Service Factory | Workhorse Sentinel ADCP;Surface Current velocity ;WHS600 600kHz;20515 | Repaired and checked at teledyne | Sébastien Lavanchy | 20230403_SN20515_finaltest.pdf, 20230403_SN20515_repairreport.pdf
2023-04-12 | 12:00 | Service Factory | Workhorse Sentinel ADCP;Surface Current velocity ;WHS600 600kHz;20515 | 20515 back from Teledyne. At EPFL | Guillaume Cunillera
2023-04-19 | 8:35 | Recovery/removal | Workhorse Sentinel ADCP;all;all;all | Out for Maintenance and 600Hz | Guillaume Cunillera
2023-04-19 | 264:00 | Maintenance | Workhorse Sentinel ADCP;all;all;all | Maintenance - cleaning. | Michael Plüss
2023-04-19 | 13:30 | Deployment/reinstalled | Workhorse Sentinel ADCP;Deep Current velocity ;WHS300 300kHz;20847 | ADCP 20360 still at teledynne | Guillaume Cunillera
2023-04-19 | 13:30 | Recovery/removal | Workhorse Sentinel ADCP;Surface Current velocity ;WHS600 600kHz;1178 | 1178 back at EAWAG | Guillaume Cunillera
2023-04-19 | 13:30 | Deployment/reinstalled | Workhorse Sentinel ADCP;Surface Current velocity ;WHS600 600kHz;20515 | ADCP swap with 1178 | Michael Plüss
2023-07-13 | 12:00 | Service Factory | Workhorse Sentinel ADCP;Deep Current velocity ;WHS300 300kHz;20360 | 20360 back from teledyne. At EPFL | Guillaume Cunillera
2023-10-18 | 17:00 | Installation | Workhorse Sentinel ADCP;Deep Current velocity ;WHS300 300kHz;20360 | New deployement, at the bottom looking up. N 45.50081°, E 006.65897 | Sébastien Lavanchy
2023-10-19 | 7:30 | Installation | Workhorse Sentinel ADCP;Deep Current velocity ;WHS300 300kHz;20360 | vmDAS started on computer LéXPLORE_01 | Sébastien Lavanchy
2023-10-19 | 11:00 | Recovery/removal | Workhorse Sentinel ADCP;all;all;all | Out for maintenance 20515 and 20847 | Guillaume Cunillera
2023-10-19 | 11:10 | Maintenance | Workhorse Sentinel ADCP;all;all;all | Cleaning mussels | Michael Plüss
2023-10-19 | 11:45 | Deployment/reinstalled | Workhorse Sentinel ADCP;all;all;all | Back in water | Guillaume Cunillera
2023-10-19 | 13:00 | Installation | Workhorse Sentinel ADCP;Deep Current velocity ;WHS300 300kHz;20360 | Check cable installation with ROV | Guillaume Cunillera
2024-01-12 | 16:00 | Other | Workhorse Sentinel ADCP;all;all;all | Vmdas software restarted | Guillaume Cunillera
2024-03-06 | 10:00 | Recovery/removal | Workhorse Sentinel ADCP;all;all;all | Maintenance - cleaning. | Jérémy Keller
2024-03-06 | 10:15 | Maintenance | Workhorse Sentinel ADCP;all;all;all | Maintenance - cleaning. | Jérémy Keller
2024-03-06 | 11:00 | Deployment/reinstalled | Workhorse Sentinel ADCP;all;all;all | Back in water after cleaning | Jérémy Keller
2024-04-07 | 18:00 | Issue | Workhorse Sentinel ADCP;all;all;all | PC1 froze. | Guillaume Cunillera
2024-04-08 | 8:00 | Repair | Workhorse Sentinel ADCP;all;all;all | PC1 restart | Guillaume Cunillera
2024-07-11 | 7:40 | Recovery/removal | Workhorse Sentinel ADCP;all;all;all | Maintenance, cleaning and deeper installation. Reinstallation aborted due to the winch of the boat (tore off attachment points) | Guillaume Cunillera
2024-07-18 | 12:00 | Other | Workhorse Sentinel ADCP;all;all;all | mooring reinstalled 17m deeper. (No cable left for a new deployment closer to the surface.). Maybe deeper than intended ? 600 should be able to measure between 25m and the surface. Not running | Guillaume Cunillera
2024-07-19 | 12:00 | Deployment/reinstalled | Workhorse Sentinel ADCP;all;all;all | new settings, 600 : 40m range (160x0,25bins) - 300 : 85m range (85x1m bins). Running now, may have to adapt the settings. | Guillaume Cunillera | 20240709_new_settings_25m
2024-07-23 | 12:00 | Recovery/removal | Workhorse Sentinel ADCP;all;all;all | recovery to measure the depth : 27.7m (top of the structure, 28m 600, 29m 300) | Guillaume Cunillera
23/072024 | 13:00 | Deployment/reinstalled | Workhorse Sentinel ADCP;all;all;all | redeployed a bit more North-West, depth is now : 26m for the 600 and 27m for the 300 | Guillaume Cunillera
SN 23656 (at EAWAG right now) that is own by the LIMNC)

## Settings
Type | Type;Parameters;model;S/N | Operator | belong to | where
Installation | Workhorse Sentinel ADCP;Surface Current velocity ;WHS600 600kHz;20515 | Guillaume Cunillera | 20515 - 600 kHz EAWAG | LéXPLORE 600
Out of order | Workhorse Sentinel ADCP;Deep Current velocity ;WHS300 300kHz;20360 | Roxane Fillion | 20360 - 300kHz | LéXPLORE 300 up at the bottom
Recovery/removal | Workhorse Sentinel ADCP;all;all;all | Matteo Gios
Deployment/reinstalled |  | Sébastien Lavanchy
Issue | Workhorse Sentinel ADCP;Surface Current velocity ;WHS600 600kHz;1178 | Floreana Miesen | 1178 - 600 kHz | at EAWAG
Repair | Workhorse Sentinel ADCP;Deep Current velocity ;WHS300 300kHz;20847 | Michael Plüss | 20847 - 300 kHz | LéXPLORE 300
Calibration Factory |  | Philippe Quetin
Calibration Field |  | Aurélien Ballu
Calibration Lab |  | Bieito Fernandez
Maintenance |  | Sebastiano Piccolroaz
Other |  | Jérémy Keller
Service Factory
|  |  | 23656 LIMNC | at EAWAG